## Sheet1
Requirements | Task | Estimation | yan | raj | srini | neel
User registration | Add additional field information to User Registration screen. * Date of birth * Address * City * State * Phone Number | 3 | 2 | 3 | 2 | 3
| Implement validation for additional fields. | 1 | 1 | 1 | 1 | 1
| Send email to user after successful registration. | 1 | 1 | 1 | 1 | 1
| Add new fields to database models. | 1 | 1 | 1 | 1 | 1
Login | Fix Session management through out the application (The system will show a message of session expire when user exceeds the particular time duration provided.). | 2 | 3 | 2 | 2 | 2
| Check for Valid subscription every time user login into application. | 1 | 1 | 1 | 1 | 1
| Admin Vs User role while login into application | 1 | 1 | 1 | 1 | 1
Profile | Add additional field information to Update profile screen. * Date of birth * Address * City * State * Phone Number | 1 | 1 | 1 | 1 | 1
| Remove New Password or Repeat New Password fields from Update profile screen. | 1 | 1 | 1 | 1 | 1
| Change password screen to change the current password. | 1 | 1 | 1 | 1 | 1
| Send email to user after changing the password. | 1 | 1 | 1 | 1 | 1
Admin | User management screen (List all the users and admin can able to update the user info based on the selection). | 3 | 3 | 3 | 2 | 3
| Question management screen (Admin can able to add/edit/delete the certification questions to database. | 8 | 5 | 5 | 8 | 8
**Add Certification screen (Admin can able to add multiple certifications to system).
History | Add Dynamic chart information for each exam record shown on the screen.