## ASQ 2.0 project plan
Status | Task Name | Start Date | End Date | Assigned To | Duration | Comments
Complete | Requirement phase | 2015-10-05 | 2015-10-09 |  | 5d
Complete | Discussion with customer | 2015-10-05 | 2015-10-06 | All | 2d
Complete | Detailed requirements document | 2015-10-07 | 2015-10-08 | All | 2d
Complete | Requirement sign off | 2015-10-09 | 2015-10-09 | All | 1d
Complete | Design Phase | 2015-10-12 | 2015-10-16 |  | 5d
Complete | Detailed design document | 2015-10-12 | 2015-10-16 | All | 5d
| Development and Testing phase | 2015-10-19 | 2015-12-24 |  | 50d
Complete | Sprint 1 | 2015-10-19 | 2015-10-30 |  | 10d
Complete | Add additional fields to the user registration page and fix the successful registration email | 2015-10-19 | 2015-10-30
Complete | Date of birth, address, city, state, phone no. | 2015-10-19 | 2015-10-21 | Srinivas Thungathurti | 3d
Complete | Unit testing for additional fields | 2015-10-21 | 2015-10-21 | Srinivas Thungathurti | 1d
Complete | Q/A testing | 2015-10-22 | 2015-10-22 | Rajesh Nerkar | 1d
Complete | Implement validation for additional fields | 2015-10-23 | 2015-10-23 | Srinivas Thungathurti | 1d
Complete | Unit testing for validation of additional fields | 2015-10-23 | 2015-10-23 | Srinivas Thungathurti | 1d
Complete | Q/A testing | 2015-10-26 | 2015-10-26 | Rajesh Nerkar | 1d
Complete | Send email to user after successful regisration | 2015-10-26 | 2015-10-28 | Ziyi Yan | 2d
Complete | Unit testing for send email to user after successful registration | 2015-10-28 | 2015-10-28 | Ziyi Yan | 1d
Complete | Q/A testing | 2015-10-29 | 2015-10-29 | Rajesh Nerkar | 1d
Complete | Add new fields to database models | 2015-10-29 | 2015-10-29 | Ziyi Yan | 1d
Complete | Unit testing for adding new fields to database models | 2015-10-29 | 2015-10-29 | Ziyi Yan | 1d
| Q/A testing | 2015-10-30 | 2015-10-30 | Rajesh Nerkar | 1d
Complete | Sprint 2 | 2015-11-02 | 2015-11-13 |  | 10d
Complete | Fix the session management through out the application and check for valid subscription | 2015-11-02 | 2015-11-11
Complete | Fix session management | 2015-11-02 | 2015-11-04 | Srinivas Thungathurti | 3d
Complete | Unit testing on fix session management | 2015-11-04 | 2015-11-04 | Srinivas Thungathurti | 1d
Complete | Q/A testing | 2015-11-05 | 2015-11-05 | Rajesh Nerkar | 1d
Complete | Check for valid subscription at each login | 2015-11-06 | 2015-11-09 | Srinivas Thungathurti | 2d
Complete | Unit Testing for valid subscription check at each login | 2015-11-09 | 2015-11-09 | Srinivas Thungathurti | 1d
Complete | Q/A testing | 2015-11-10 | 2015-11-10 | Rajesh Nerkar | 1d
Complete | Admin vs user role while login | 2015-11-11 | 2015-11-12 | Ziyi Yan | 2d
Complete | Unit testing for admin vs user role while login | 2015-11-12 | 2015-11-12 | Ziyi Yan | 1d
Complete | Q/A testing | 2015-11-13 | 2015-11-13 | Rajesh Nerkar | 1d
Complete | Sprint 3 | 2015-11-16 | 2015-11-27 |  | 10d
Complete | Add additional fields, Removing new password or repeat new password field from update profile screen | 2015-11-16 | 2015-11-27
Complete | Date of birth, Address, city, state, phone no. | 2015-11-16 | 2015-11-17 | Srinivas Thungathurti | 1d
Complete | Unit testing | 2015-11-17 | 2015-11-17 | Srinivas Thungathurti | 1d
Complete | Q/A testing | 2015-11-18 | 2015-11-18 | Rajesh Nerkar | 1d
Complete | Remove new password and repeat new password field | 2015-11-18 | 2015-11-19 | Srinivas Thungathurti | 1d
Complete | Unit testing | 2015-11-19 | 2015-11-19 | Srinivas Thungathurti | 1d
Complete | Q/A testing | 2015-11-20 | 2015-11-20 | Rajesh Nerkar | 1d
Complete | Change password screen to change the current password | 2015-11-23 | 2015-11-24 | Ziyi Yan | 1d
Complete | Unit testing | 2015-11-24 | 2015-11-24 | Ziyi Yan | 1d
Complete | Q/A testing | 2015-11-24 | 2015-11-24 | Rajesh Nerkar | 1d
Complete | Send email to user after changing the password | 2015-11-25 | 2015-11-26 | Ziyi Yan | 1d
Complete | Unit testing | 2015-11-26 | 2015-11-26 | Ziyi Yan | 1d
Complete | Q/A testing | 2015-11-27 | 2015-11-27 | Rajesh Nerkar | 1d
Complete | Sprint 4 | 2015-11-30 | 2015-12-11 |  | 10d
Complete | Admin makes changes to user management screen (by updating the user info based on selection) and question management screen (can add/delete/edit certification questions to database) | 2015-11-30 | 2015-12-11
Complete | Admin updates the user info based on the selection | 2015-11-30 | 2015-12-02 | Srinivas Thungathurti | 3d
Complete | Unit testing | 2015-12-02 | 2015-12-02 | Srinivas Thungathurti | 1d
Complete | Q/A Testing | 2015-12-03 | 2015-12-03 | Rajesh Nerkar | 1d
Complete | Admin adds/deletes/edits the certification questions to database | 2015-12-04 | 2015-12-09 | Ziyi Yan | 4d
Complete | Unit testing | 2015-12-09 | 2015-12-09 | Ziyi Yan | 1d
Complete | Q/A Testing | 2015-12-10 | 2015-12-11 | Rajesh Nerkar | 2d
Complete | Sprint 5 | 2015-12-14 | 2015-12-24 |  | 10d
Complete | Adding dynamic chart for each exam record shown on the screen | 2015-12-14 | 2015-12-18 | Srinivas Thungathurti | 6d
Complete | Unit testing | 2015-12-18 | 2015-12-18 | Srinivas Thungathurti | 1d
Complete | Q/A Testing | 2015-12-21 | 2015-12-24 | Rajesh Nerkar | 4d