## WBS
TOTAL +10%
[7 empty] | (66) = 270 hrs | List Assumptions
TOTAL
(59) = 236 hrs
Project Mgmt
(8) = 32 hrs
ASQ CSQE Web App
(51) = 204 hrs
|  | 1. Front End | [5 empty] | 2. Backend |  |  | 3. Database
|  | (24) = 96 hrs | [5 empty] | (7) = 28 hrs |  |  | (20) = 80 hrs
1.1 Log In/ Log out | 1.2 Create User Account |  | 1.3 Practice Mode |  | 1.4 Exam Mode | 1.5. Front View Template | 2.1. Log In/ Log Out Validation | 2.2. Create Account | 2.3. Query Db and send results to frontend | 3.1. Create Db |  | 3.2. Upload Questions
(1) | (1) display HTML form |  |  | (1) |  | (5) user friendly, aesthetically pleasing, alignment, browser compatible | (2) cookies, sessions, 3rd party library, (encryption not needed) | (2) map to db, check duplicate accounts, send confirmation email | (3) | (1) |  | (13) can copy and paste pdf, transfer manually. Graphs copied manually. May be done faster with jSON or XML script
1.1.1. Req'd fields Validation | 1.2.1. Format Validation (email + fields req) |  | 1.3.1. Mode Selection |  | 1.4.1. Mode Selection |  |  |  |  | 3.1.1. Db schema |  | 3.2.1. Save Results
(1) | (1) |  |  | (5) select number of questions, send query to Db to 2.3. | [5 empty] | (5)complete tables for holding questions, profiles, exam results, encryption for password |  | (1)
| 1.2.2. Password Validation |  | 1.3.2. Display Questions |  | 1.4.2. Display Questions
| (1) |  |  | (2) one question per page vs all questions together. Add ability to jump to desired question?
|  |  | 1.3.3. Grade Questions & Display Results |  | 1.4.3. Grade Questions & Display Results
(5) move grading to backend and display results on frontend
1.4.4. Countdown Timer
(1)

## Time
WP ID | Activity/Task Name | SubActivity/SubTask | Owner | Start | End | Time | Status
1.1. | Log In/Log out | Design | Jaime/neeru | 2015-07-06 | 2015-07-06 |  | inprogress | logout very end of project
1.1. | Log In/Log out | Code | Harry | 2015-07-06 | 2015-07-06
1.1. | Log In/Log out | Test | Nikitha | 2015-07-07 | 2015-07-07 |  | inprogress
1.1.1 | Req'd fields Validation | Design | Jaime/neeru
1.1.1 | Req'd fields Validation | Code | Harry | 2015-07-07 | 2015-07-07 |  | inprogress
1.1.1 | Req'd fields Validation | Test | Nikitha | 2015-07-08 | 2015-07-08 |  | inprogress
1.2. | Create User Account | Design | Jaime/neeru
1.2. | Create User Account | Code | Harry | 2015-07-08 | 2015-07-08
1.2. | Create User Account | Test | Nikitha | 2015-07-09 | 2015-07-09
1.2.1 | Format Validation (email + fields req) | Design | Jaime/neeru
1.2.1 | Format Validation (email + fields req) | Code | Harry | 2015-07-09 | 2015-07-09
1.2.1 | Format Validation (email + fields req) | Test | Nikitha | 2015-07-10 | 2015-07-10
1.2.2 | Password Validation | Design | Jaime/neeru
1.2.2 | Password Validation | Code | Harry | 2015-07-10 | 2015-07-10
1.2.2 | Password Validation | Test | Nikitha | 2015-07-13 | 2015-07-13
1.3. | Practice Mode | Design | Jaime/neeru
1.3. | Practice Mode | Code | Harry | 2015-07-13 | 2015-07-13
1.3. | Practice Mode | Test | Nikitha | 2015-07-23 | 2015-07-23
1.3.1 | ModeSelection | Design | Jaime/neeru
1.3.1 | ModeSelection | Code | Harry | 2015-07-17 | 2015-07-17
1.3.1 | ModeSelection | Test | Nikitha | 2015-07-24 | 2015-07-24
1.3.2 | Display Questions | Design | Jaime/neeru
1.3.2 | Display Questions | Code | Harry | 2015-07-20 | 2015-07-20
1.3.2 | Display Questions | Test | Nikitha | 2015-07-26 | 2015-07-26
1.3.3 | Grade Questions & Display Results | Design | Jaime/neeru
1.3.3 | Grade Questions & Display Results | Code | Harry | 2015-07-21 | 2015-07-22
1.3.3 | Grade Questions & Display Results | Test | Nikitha | 2015-07-27 | 2015-07-27
1.4. | Exam Mode | Design | Jaime/neeru
1.4. | Exam Mode | Code | Harry | 2015-07-23 | 2015-07-23
1.4. | Exam Mode | Test | Nikitha | 2015-07-28 | 2015-07-28
1.4.1 | Mode Selection | Design | Jaime/neeru
1.4.1 | Mode Selection | Code | Harry | 2015-07-24 | 2015-07-24
1.4.1 | Mode Selection | Test | Nikitha | 2015-07-28 | 2015-07-28
1.4.2 | Display Questions | Design | Jaime/neeru
1.4.2 | Display Questions | Code | Harry | 2015-07-27 | 2015-07-27
1.4.2 | Display Questions | Test | Nikitha | 2015-07-29 | 2015-07-29
1.4.3 | Grade Questions & Display Results | Design | Jaime/neeru
1.4.3 | Grade Questions & Display Results | Code | Harry | 2015-07-29 | 2015-07-29
1.4.3 | Grade Questions & Display Results | Test | Nikitha | 2015-07-30 | 2015-07-30
1.4.4 | Countdown Timer | Design | Jaime/neeru
1.4.4 | Countdown Timer | Code | Harry | 2015-07-30 | 2015-07-30
1.4.4 | Countdown Timer | Test | Nikitha | 2015-07-31 | 2015-07-31
1.5. | Front View Template | Design | Jaime/neeru
1.5. | Front View Template | Code | Harry | 2015-07-31 | 2015-08-04
1.5. | Front View Template | Test | Nikitha | 2015-08-05 | 2015-08-06
2.1. | Log In/Log Out Validation | Design | Jaime/neeru
2.1. | Log In/Log Out Validation | Code | Harry | 2015-07-13 | 2015-07-13
2.1. | Log In/Log Out Validation | Test | Nikitha | 2015-07-14 | 2015-07-14
2.2. | Create Account | Design | Jaime/neeru
2.2. | Create Account | Code | Harry | 2015-07-23 | 2015-07-23
2.2. | Create Account | Test | Nikitha
2.3. | Query Db and send results to frontend | Design | Jaime/neeru
2.3. | Query Db and send results to frontend | Code | Harry | 2015-07-24 | 2015-07-28
2.3. | Query Db and send results to frontend | Test | Nikitha
3.1. | Create Db | Design | Jaime/neeru
3.1. | Create Db | Code | Harry | 2015-07-14 | 2015-07-15
3.1. | Create Db | Test | Nikitha | 2015-07-15 | 2015-07-15
3.1.1 | Db schema | Design | Jaime/neeru
3.1.1 | Db schema | Code | Harry | 2015-07-15 | 2015-07-16
3.1.1 | Db schema | Test | Nikitha | 2015-07-17 | 2015-07-17
3.2. | Upload Questions | Design | Jaime/neeru
3.2. | Upload Questions | Code | Harry/neeru | 2015-07-16 | 2015-07-22
3.2. | Upload Questions | Test | Nikitha
3.2.1 | Save Results | Design | Jaime/neeru
3.2.1 | Save Results | Code | Harry | 2015-07-27 | 2015-07-28
3.2.1 | Save Results | Test | Nikitha

## DEV MODEL
INCREMENTAL DEVELOPMENT MODEL