## Instructions
Work Breakdown Structure (WBS)
Instructions: This template presents a standard Work Breakdown Structure (WBS) design for planning and monitoring projects. It provides a framework for developing a plan/schedule for any project.
To create a schedule in the selected project management tool, refer to the WBS template and perform the following steps:
1. Set up the Project Initiation, Planning, Execution, Controlling and Closing Phases as the 2nd Level of the WBS for Process-type WBS or Components for Product-type WBS
Note: the Project Definition is the 1st Level of the WBS.
2. Review the 3rd Level WBS elements listed under each project phase and:
a. Delete those not relevant to your project.
b. Add new elements (add appropriate number of "Other" boxes and rename)
3. Incorporate WBS into project management tool.
You must have "Tools/Options/View/Comment Indicator Only" checked in order to see on-line help.
PROJECT INFORMATION
Project Description | Develop a web application that simulates the ASQ CSQE exam
Project Definition
Project Manager | Neeru Bansal
Note on A13: Name of project from
Note on A14: Short description of the project

## WBS Template
Work Breakdown Structure
PROJECT SYSTEM | [8 empty] | OTHER PROJECT TOOLS
Level 1 WBS | [5 empty] | 0. ASQ CSQE Web App |  |  | Project Name
Level 2 WBS | 1. Front-End |  |  |  |  | 2. Back-End | 3. Database |  | Phase/ Component
Level 3 WBS | 1.1 User Log-in/logout | 1.2 Create User Account | 1.3 Practice Mode" | 1.4 Exam Mode Mode" | 1.5 Front View Template Mode" | 2.1 Log In/Log Out Validation | 3.1 Create Db | 3.2 Upload Questions | Task
| 1.1.1 Req'd fields Validation | 1.2.1 Format Validation (email + fields req) | 1.3.1 ModeSelection | 1.4.1 Mode Selection |  | 2.2 Create Account | 3.1.1 Db schema | 3.2.1 Save Results
|  | 1.2.2 Password Validation | 1.3.2 Display Questions | 1.4.2 Display Questions |  | 2.3 Query Db and send results to frontend
|  |  | 1.3.3 Grade Questions & Display Results | 1.4.3 Grade Questions & Display Results
1.4.4 Countdown Timer

## Effort_estimation
WP Task ID | Description | Asssumptions | Unit of Size | Estimation
2.1.1 | Requirements
1 | Gather req | provided by the customer | hours | 4
2 | Review req |  | hours | 2
3 | Prioritize req |  | hours | 1
2.1.1 | Subtotal WP |  |  | 7
WP Task ID | Description | Asssumptions | Unit of Size | Estimation
2.1.2
1 |  |  | hours
2.1.2 | Subtotal WP |  |  | 0